## Slide 1: Site Permitting Process and Ongoing Requirements
Molly Staats
November 9, 2015

## Slide 2: Land Status Review
BLM Mapper/ State Mapper/ Yukon Lands Viewer
Case Reviews (non state/federal lands)
Agency Internal Land Status Review

## Slide 3: Who are we permitting with?
Secondary:
NSB (1 month)
Native Villages (days to months)
Military (6 months +)
Primary:
Federal
  BLM
    NPR-A (6 months)
    Fairbanks (9 months)
    Anchorage (1 ½ years +)
  FWS (1 ½ years +)
  NPS (5 months)
State
  DNR (2-3 months)
Other
  Native Corps (1 month +)
  Private (1 day to few weeks)

## Slide 4: Who are we permitting with?
Secondary:
Yukon Highways (1 month +)
BC Highways (3 months +)
Primary:
  Sci and Explorers (3 months +)
Territory/Province
  Yukon Lands (6 months +)
  BC Lands (3 months)
  National Park (3 months +)
  Provincial/Territorial Park
Other
  First Nations (1 month +)
  Private
Notes: ----- Meeting Notes (10/30/15 16:37) -----
Overarching Sci and Expor

## Slide 5: Permitting Process
Process:
Request internal land status review
In-person meeting
Official request letter and/or Application
  Primary, alternates, and descope
  Applications range in size/detail
Monthly check-in (Nagging!)
Permit and Payment
Delays:
NEPA
Archeological potential/ Cultural sensitivity (Install site visits)
Wilderness and Wildlife
Ambiguous land status or boundaries
Multiple permitting agencies
Notes: ----- Meeting Notes (10/30/15 16:37) -----
* NEPA-environment (national environmental policy act
* Sensitivity: Cost recovery, scheduling staff to be on site during or before (BLM and NPS)

## Slide 6: Landowner Breakdown
Chart: 
| Military | NPS | BLM Fairbanks | BLM Anchorage | BLM NPR-A | Private | FWS | Native Village/ Corp | DNR/State
 | 1 | 4 | 12 | 14 | 16 | 16 | 19 | 23 | 58
26%

## Slide 7: Landowner Breakdown
Chart: 
| BC Lands | BC Highways | Provincial Park | First Nations/ Villages | NPS | Yukon Lands
 | 3 | 2 | 2 | 6 | 4 | 27

## Slide 8: Status
301 Total Sites*
110 Certified
  46 Installed
  65 Existing
63 Permitted
  15 alternates
70 Application Submitted
  18 alternates
27 Require Permitting
  But 10 descoped
25 AEC, AT, AVO
6 require recon
  But 4 descoped

## Slide 9: Next Steps
2016 Installation Permitting Stats
  91 Sites (9 Descoped)
    19 Existing or Co-locates
    21 Permit Accepted
    35 Permit Submitted
    16 Need Permitting